## MDR Import
EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import | EngiCite Master Document Register Import
Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD. | Required columns are marked *. Keep the headings unchanged. Dates must be real Excel dates or YYYY-MM-DD.
Document Number * | Title * | Discipline * | Document Type * | Planned Submission Date * | Planned Final Date | Required Issue Status | Responsible Party | Progress Weight | Area | System | Work Package
HMK-26-01-PRO-BAS-0001 | Process Design Basis | Process | Report | 2026-07-29 | 2026-08-05 | Issued for Approval (IFA) | EPCIC Contractor – Process Engineering | 2 | General | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-CRI-0001 | Process Design Criteria | Process | Specification | 2026-07-29 | 2026-08-05 | Issued for Approval (IFA) | EPCIC Contractor – Process Engineering | 1 | General | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-PFD-0001 | Process Flow Diagram – Inlet Manifold and Separation | Process | Drawing | 2026-08-05 | 2026-08-12 | Issued for Design (IFD) | EPCIC Contractor – Process Engineering | 2 | Process Area | Inlet & Separation | WP-01 Process Engineering
HMK-26-01-PRO-PFD-0002 | Process Flow Diagram – Crude Oil Treatment and Export | Process | Drawing | 2026-08-05 | 2026-08-12 | Issued for Design (IFD) | EPCIC Contractor – Process Engineering | 2 | Process Area | Oil Treatment & Export | WP-01 Process Engineering
HMK-26-01-PRO-PFD-0003 | Process Flow Diagram – Produced Water Treatment | Process | Drawing | 2026-08-05 | 2026-08-12 | Issued for Design (IFD) | EPCIC Contractor – Process Engineering | 1 | Process Area | Produced Water | WP-01 Process Engineering
HMK-26-01-PRO-PFD-0004 | Process Flow Diagram – Utilities and Support Systems | Process | Drawing | 2026-08-05 | 2026-08-12 | Issued for Design (IFD) | EPCIC Contractor – Process Engineering | 1 | Utilities | Utilities | WP-01 Process Engineering
HMK-26-01-PRO-HMB-0001 | Heat and Material Balance | Process | Calculation | 2026-08-05 | 2026-08-12 | Issued for Approval (IFA) | EPCIC Contractor – Process Engineering | 2 | Process Area | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-UBL-0001 | Utility Consumption and Balance | Process | Calculation | 2026-08-12 | 2026-08-19 | Issued for Approval (IFA) | EPCIC Contractor – Process Engineering | 1 | Utilities | Utilities | WP-01 Process Engineering
HMK-26-01-PRO-LST-0001 | Process Equipment List | Process | List | 2026-08-05 | 2026-08-12 | Issued for Approval (IFA) | EPCIC Contractor – Process Engineering | 1 | General | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-LST-0002 | Process Line List | Process | List | 2026-08-12 | 2026-08-19 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 2 | General | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-PID-0001 | P&ID – Inlet Manifold and Pig Receiver | Process | Drawing | 2026-08-12 | 2026-08-19 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 2 | Process Area | Inlet & Separation | WP-01 Process Engineering
HMK-26-01-PRO-PID-0002 | P&ID – Production Separators | Process | Drawing | 2026-08-12 | 2026-08-19 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 2 | Process Area | Inlet & Separation | WP-01 Process Engineering
HMK-26-01-PRO-PID-0003 | P&ID – Crude Oil Transfer and Export | Process | Drawing | 2026-08-19 | 2026-08-26 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 2 | Export Area | Oil Treatment & Export | WP-01 Process Engineering
HMK-26-01-PRO-PID-0004 | P&ID – Produced Water Collection and Treatment | Process | Drawing | 2026-08-19 | 2026-08-26 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 2 | Process Area | Produced Water | WP-01 Process Engineering
HMK-26-01-PRO-PID-0005 | P&ID – Fuel Gas System | Process | Drawing | 2026-08-19 | 2026-08-26 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 1 | Utilities | Fuel Gas | WP-01 Process Engineering
HMK-26-01-PRO-PID-0006 | P&ID – Flare and Blowdown System | Process | Drawing | 2026-08-19 | 2026-08-26 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 2 | Flare Area | Flare & Blowdown | WP-01 Process Engineering
HMK-26-01-PRO-PID-0007 | P&ID – Open and Closed Drain Systems | Process | Drawing | 2026-08-19 | 2026-08-26 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 1 | Process Area | Drain Systems | WP-01 Process Engineering
HMK-26-01-PRO-PID-0008 | P&ID – Chemical Injection Systems | Process | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Process Engineering | 1 | Process Area | Chemical Injection | WP-01 Process Engineering
HMK-26-01-PRO-DAT-0001 | Process Datasheet – Production Separators | Process | Datasheet | 2026-08-12 | 2026-08-19 | Issued for Procurement (IFP) | EPCIC Contractor – Process Engineering | 1 | Process Area | Inlet & Separation | WP-02 Procurement
HMK-26-01-PRO-DAT-0002 | Process Datasheet – Crude Oil Transfer Pumps | Process | Datasheet | 2026-08-12 | 2026-08-19 | Issued for Procurement (IFP) | EPCIC Contractor – Process Engineering | 1 | Export Area | Oil Treatment & Export | WP-02 Procurement
HMK-26-01-PRO-DAT-0003 | Process Datasheet – Produced Water Pumps | Process | Datasheet | 2026-08-19 | 2026-08-26 | Issued for Procurement (IFP) | EPCIC Contractor – Process Engineering | 1 | Process Area | Produced Water | WP-02 Procurement
HMK-26-01-PRO-DAT-0004 | Process Datasheet – Storage and Drain Vessels | Process | Datasheet | 2026-08-19 | 2026-08-26 | Issued for Procurement (IFP) | EPCIC Contractor – Process Engineering | 1 | Process Area | Drain Systems | WP-02 Procurement
HMK-26-01-PRO-CAL-0001 | Relief, Blowdown and Flare Load Study | Process | Calculation | 2026-08-19 | 2026-08-26 | Issued for Approval (IFA) | EPCIC Contractor – Process Engineering | 2 | Flare Area | Flare & Blowdown | WP-01 Process Engineering
HMK-26-01-PRO-CAL-0002 | Process Hydraulic Calculations | Process | Calculation | 2026-08-26 | 2026-09-02 | Issued for Approval (IFA) | EPCIC Contractor – Process Engineering | 2 | Process Area | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-PHI-0001 | Process Control and Operating Philosophy | Process | Philosophy | 2026-08-19 | 2026-08-26 | Issued for Approval (IFA) | EPCIC Contractor – Process Engineering | 1 | General | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-PHI-0002 | Safeguarding, Shutdown and Depressurisation Philosophy | Process | Philosophy | 2026-08-19 | 2026-08-26 | Issued for Safety Review | EPCIC Contractor – Process Engineering | 2 | General | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-RPT-0001 | HAZOP Review Report | Process | Report | 2026-09-02 | 2026-09-09 | Issued for HAZOP Review | EPCIC Contractor – Process Engineering | 2 | General | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-RPT-0002 | HAZOP Action Close-out Report | Process | Report | 2026-09-09 | 2026-09-16 | Approved / Final | EPCIC Contractor – Process Engineering | 1 | General | Project-wide | WP-01 Process Engineering
HMK-26-01-PRO-MAN-0001 | Process Operating Manual | Process | Manual | 2026-10-07 | 2026-10-14 | Issued for Operations | EPCIC Contractor – Process Engineering | 2 | General | Project-wide | WP-07 Commissioning & Handover
HMK-26-01-PRO-MAN-0002 | Process Start-up and Shutdown Manual | Process | Manual | 2026-10-07 | 2026-10-14 | Issued for Start-up | EPCIC Contractor – Process Engineering | 1 | General | Project-wide | WP-07 Commissioning & Handover
HMK-26-01-PIP-BAS-0001 | Piping Design Basis | Piping | Report | 2026-07-29 | 2026-08-05 | Issued for Approval (IFA) | EPCIC Contractor – Piping Engineering | 2 | General | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-SPE-0001 | Piping Materials Specification | Piping | Specification | 2026-08-05 | 2026-08-12 | Issued for Approval (IFA) | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-SPE-0002 | Piping Material Class Specification | Piping | Specification | 2026-08-05 | 2026-08-12 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | General | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-SPE-0003 | Valve Specification | Piping | Specification | 2026-08-12 | 2026-08-19 | Issued for Procurement (IFP) | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-02 Procurement
HMK-26-01-PIP-SPE-0004 | Piping Insulation Specification | Piping | Specification | 2026-08-12 | 2026-08-19 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-SPE-0005 | Piping Painting and Protective Coating Specification | Piping | Specification | 2026-08-12 | 2026-08-19 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-LST-0001 | Piping Line List | Piping | List | 2026-08-12 | 2026-08-19 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | General | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-LST-0002 | Valve List | Piping | List | 2026-08-19 | 2026-08-26 | Issued for Procurement (IFP) | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-02 Procurement
HMK-26-01-PIP-LST-0003 | Piping Specialty Items List | Piping | List | 2026-08-19 | 2026-08-26 | Issued for Procurement (IFP) | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-02 Procurement
HMK-26-01-PIP-DWG-0001 | Overall Equipment and Piping Plot Plan | Piping | Drawing | 2026-08-05 | 2026-08-12 | Issued for Approval (IFA) | EPCIC Contractor – Piping Engineering | 2 | Site-wide | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-DWG-0002 | Process Area Piping General Arrangement | Piping | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Process Area | Inlet & Separation | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-DWG-0003 | Utilities Area Piping General Arrangement | Piping | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Utilities | Utilities | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-DWG-0004 | Main Pipe Rack Piping Layout | Piping | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Process Area | Pipe Rack | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-DWG-0005 | Underground Piping and Drainage Layout | Piping | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Site-wide | Underground Services | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-SCH-0001 | Piping Tie-in Schedule | Piping | Schedule | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 1 | Site-wide | Tie-ins | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-CAL-0001 | Pipe Stress Calculation – Inlet and Export Lines | Piping | Calculation | 2026-09-02 | 2026-09-09 | Issued for Approval (IFA) | EPCIC Contractor – Piping Engineering | 2 | Process Area | Inlet & Export | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-CAL-0002 | Pipe Stress Calculation – Pump Suction and Discharge | Piping | Calculation | 2026-09-02 | 2026-09-09 | Issued for Approval (IFA) | EPCIC Contractor – Piping Engineering | 2 | Process Area | Oil Transfer | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-CAL-0003 | Pipe Stress Calculation – Flare and Blowdown Headers | Piping | Calculation | 2026-09-02 | 2026-09-09 | Issued for Approval (IFA) | EPCIC Contractor – Piping Engineering | 2 | Flare Area | Flare & Blowdown | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-CAL-0004 | Pipe Stress Calculation – Utility Headers | Piping | Calculation | 2026-09-09 | 2026-09-16 | Issued for Approval (IFA) | EPCIC Contractor – Piping Engineering | 1 | Utilities | Utilities | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-RPT-0001 | Piping Flexibility and Stress Analysis Summary | Piping | Report | 2026-09-09 | 2026-09-16 | Approved / Final | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-DWG-0006 | Standard Pipe Support Details | Piping | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 1 | Site-wide | Pipe Supports | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-DWG-0007 | Critical and Special Pipe Support Drawings | Piping | Drawing | 2026-09-09 | 2026-09-16 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Site-wide | Pipe Supports | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-ISO-0001 | Piping Isometrics – Inlet Manifold | Piping | Drawing | 2026-09-16 | 2026-09-23 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 3 | Process Area | Inlet | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-ISO-0002 | Piping Isometrics – Separation System | Piping | Drawing | 2026-09-16 | 2026-09-23 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 3 | Process Area | Separation | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-ISO-0003 | Piping Isometrics – Crude Oil Export | Piping | Drawing | 2026-09-16 | 2026-09-23 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 3 | Export Area | Oil Export | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-ISO-0004 | Piping Isometrics – Produced Water | Piping | Drawing | 2026-09-23 | 2026-09-30 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Process Area | Produced Water | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-ISO-0005 | Piping Isometrics – Fuel Gas | Piping | Drawing | 2026-09-23 | 2026-09-30 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Utilities | Fuel Gas | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-ISO-0006 | Piping Isometrics – Flare and Blowdown | Piping | Drawing | 2026-09-23 | 2026-09-30 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Flare Area | Flare & Blowdown | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-ISO-0007 | Piping Isometrics – Open and Closed Drains | Piping | Drawing | 2026-09-23 | 2026-09-30 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 2 | Process Area | Drain Systems | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-ISO-0008 | Piping Isometrics – Chemical Injection | Piping | Drawing | 2026-09-30 | 2026-10-07 | Approved for Construction (AFC) | EPCIC Contractor – Piping Engineering | 1 | Process Area | Chemical Injection | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-MTO-0001 | Bulk Piping Material Take-Off | Piping | Material Take-Off | 2026-09-09 | 2026-09-16 | Issued for Procurement (IFP) | EPCIC Contractor – Piping Engineering | 2 | General | Project-wide | WP-02 Procurement
HMK-26-01-PIP-PRC-0001 | Piping Fabrication and Installation Procedure | Piping | Procedure | 2026-09-16 | 2026-09-23 | Issued for Construction (IFC) | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-04 Piping Engineering & Construction
HMK-26-01-PIP-PRC-0002 | Piping Pressure Testing, Flushing and Reinstatement Procedure | Piping | Procedure | 2026-09-30 | 2026-10-07 | Issued for Commissioning | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-07 Commissioning & Handover
HMK-26-01-PIP-PRC-0003 | Piping Redline and As-Built Preparation Procedure | Piping | Procedure | 2026-10-18 | 2026-10-21 | Redline / Marked-up As-Built | EPCIC Contractor – Piping Engineering | 1 | General | Project-wide | WP-07 Commissioning & Handover
HMK-26-01-STR-BAS-0001 | Structural Design Basis | Structural | Report | 2026-07-29 | 2026-08-05 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 2 | General | Project-wide | WP-03 Civil & Structural
HMK-26-01-STR-CRI-0001 | Civil and Structural Design Criteria | Structural | Specification | 2026-07-29 | 2026-08-05 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 1 | General | Project-wide | WP-03 Civil & Structural
HMK-26-01-STR-RPT-0001 | Topographical Survey Report | Structural | Report | 2026-08-05 | 2026-08-12 | Approved / Final | EPCIC Contractor – Structural Engineering | 1 | Site-wide | Site Development | WP-03 Civil & Structural
HMK-26-01-STR-RPT-0002 | Geotechnical Investigation Report | Structural | Report | 2026-08-05 | 2026-08-12 | Approved / Final | EPCIC Contractor – Structural Engineering | 2 | Site-wide | Foundations | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0001 | Site Grading and Drainage Design Calculation | Structural | Calculation | 2026-08-12 | 2026-08-19 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 1 | Site-wide | Site Development | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0001 | Site Grading, Roads and Drainage Layout | Structural | Drawing | 2026-08-19 | 2026-08-26 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 2 | Site-wide | Site Development | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0002 | Overall Foundation Key Plan | Structural | Drawing | 2026-08-19 | 2026-08-26 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 1 | Site-wide | Foundations | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0002 | Production Separator Foundation Calculation | Structural | Calculation | 2026-08-19 | 2026-08-26 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 2 | Process Area | Separation | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0003 | Production Separator Foundation GA and Details | Structural | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 2 | Process Area | Separation | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0003 | Crude Oil Transfer Pump Foundation Calculation | Structural | Calculation | 2026-08-19 | 2026-08-26 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 1 | Export Area | Oil Export | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0004 | Pump Foundation GA and Details | Structural | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 1 | Process Area | Pumps | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0004 | Storage and Drain Vessel Foundation Calculation | Structural | Calculation | 2026-08-26 | 2026-09-02 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 1 | Process Area | Storage & Drains | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0005 | Storage and Drain Vessel Foundation Details | Structural | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 1 | Process Area | Storage & Drains | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0005 | Main Pipe Rack Structural Analysis and Design | Structural | Calculation | 2026-08-26 | 2026-09-02 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 2 | Process Area | Pipe Rack | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0006 | Main Pipe Rack Foundation Layout and Details | Structural | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 2 | Process Area | Pipe Rack | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0007 | Main Pipe Rack Structural Steel GA | Structural | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 2 | Process Area | Pipe Rack | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0008 | Main Pipe Rack Structural Steel Fabrication Details | Structural | Drawing | 2026-09-09 | 2026-09-16 | Issued for Fabrication (IFF) | EPCIC Contractor – Structural Engineering | 2 | Process Area | Pipe Rack | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0006 | Equipment Access Platforms Structural Calculation | Structural | Calculation | 2026-09-02 | 2026-09-09 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 1 | Process Area | Access Platforms | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0009 | Equipment Access Platforms GA and Details | Structural | Drawing | 2026-09-09 | 2026-09-16 | Issued for Fabrication (IFF) | EPCIC Contractor – Structural Engineering | 2 | Process Area | Access Platforms | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0007 | Equipment Shelter Structural Calculation | Structural | Calculation | 2026-09-02 | 2026-09-09 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 1 | Utilities | Equipment Shelter | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0010 | Equipment Shelter GA and Fabrication Details | Structural | Drawing | 2026-09-09 | 2026-09-16 | Issued for Fabrication (IFF) | EPCIC Contractor – Structural Engineering | 1 | Utilities | Equipment Shelter | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0008 | Substation and Control Building Structural Calculation | Structural | Calculation | 2026-08-26 | 2026-09-02 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 2 | Buildings | Electrical Buildings | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0011 | Substation and Control Building Foundation and Frame Details | Structural | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 2 | Buildings | Electrical Buildings | WP-03 Civil & Structural
HMK-26-01-STR-CAL-0009 | Flare Stack Foundation Calculation | Structural | Calculation | 2026-09-02 | 2026-09-09 | Issued for Approval (IFA) | EPCIC Contractor – Structural Engineering | 2 | Flare Area | Flare & Blowdown | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0012 | Flare Stack and Knockout Drum Foundation Details | Structural | Drawing | 2026-09-09 | 2026-09-16 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 2 | Flare Area | Flare & Blowdown | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0013 | Cable Tray and Electrical Equipment Support Foundations | Structural | Drawing | 2026-09-09 | 2026-09-16 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 1 | Site-wide | Electrical Supports | WP-03 Civil & Structural
HMK-26-01-STR-SCH-0001 | Foundation, Anchor Bolt and Reinforcement Schedule | Structural | Schedule | 2026-09-09 | 2026-09-16 | Approved for Construction (AFC) | EPCIC Contractor – Structural Engineering | 1 | Site-wide | Foundations | WP-03 Civil & Structural
HMK-26-01-STR-MTO-0001 | Concrete and Reinforcement Material Take-Off | Structural | Material Take-Off | 2026-09-02 | 2026-09-09 | Issued for Procurement (IFP) | EPCIC Contractor – Structural Engineering | 1 | General | Project-wide | WP-02 Procurement
HMK-26-01-STR-MTO-0002 | Structural Steel Material Take-Off | Structural | Material Take-Off | 2026-09-09 | 2026-09-16 | Issued for Procurement (IFP) | EPCIC Contractor – Structural Engineering | 1 | General | Project-wide | WP-02 Procurement
HMK-26-01-STR-PRC-0001 | Structural Steel Fabrication and Erection Procedure | Structural | Procedure | 2026-09-16 | 2026-09-23 | Issued for Construction (IFC) | EPCIC Contractor – Structural Engineering | 1 | General | Project-wide | WP-03 Civil & Structural
HMK-26-01-STR-PRC-0002 | Concrete Works and Foundation Construction Procedure | Structural | Procedure | 2026-09-16 | 2026-09-23 | Issued for Construction (IFC) | EPCIC Contractor – Structural Engineering | 1 | General | Project-wide | WP-03 Civil & Structural
HMK-26-01-STR-DWG-0014 | Civil and Structural As-Built Drawings | Structural | Drawing | 2026-10-21 | 2026-10-21 | Final As-Built | EPCIC Contractor – Structural Engineering | 2 | Site-wide | Project-wide | WP-07 Commissioning & Handover
HMK-26-01-ELE-BAS-0001 | Electrical Design Basis | Electrical | Report | 2026-07-29 | 2026-08-05 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 2 | General | Project-wide | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-PHI-0001 | Electrical Generation and Distribution Philosophy | Electrical | Philosophy | 2026-07-29 | 2026-08-05 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 1 | General | Project-wide | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-LST-0001 | Electrical Load List | Electrical | List | 2026-08-05 | 2026-08-12 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 2 | General | Project-wide | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-LST-0002 | Electrical Consumers and Equipment List | Electrical | List | 2026-08-05 | 2026-08-12 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 1 | General | Project-wide | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-SLD-0001 | Medium Voltage Single Line Diagram | Electrical | Drawing | 2026-08-12 | 2026-08-19 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 2 | Electrical Substation | MV Distribution | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-SLD-0002 | Low Voltage Single Line Diagram | Electrical | Drawing | 2026-08-12 | 2026-08-19 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 2 | Electrical Substation | LV Distribution | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-SLD-0003 | Essential and Emergency Power Single Line Diagram | Electrical | Drawing | 2026-08-19 | 2026-08-26 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 1 | Electrical Substation | Emergency Power | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-CAL-0001 | Electrical Load Flow Study | Electrical | Calculation | 2026-08-12 | 2026-08-19 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 2 | General | Power System | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-CAL-0002 | Short Circuit Study | Electrical | Calculation | 2026-08-12 | 2026-08-19 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 2 | General | Power System | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-CAL-0003 | Motor Starting Study | Electrical | Calculation | 2026-08-19 | 2026-08-26 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 1 | General | Power System | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-CAL-0004 | Protection Coordination and Relay Setting Study | Electrical | Calculation | 2026-08-26 | 2026-09-02 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 2 | General | Protection System | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-CAL-0005 | Earthing and Lightning Protection Calculation | Electrical | Calculation | 2026-08-19 | 2026-08-26 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 2 | General | Earthing & Lightning | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DWG-0001 | Site Earthing and Lightning Protection Layout | Electrical | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 2 | Site-wide | Earthing & Lightning | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-CAL-0006 | Lighting Level Calculation | Electrical | Calculation | 2026-08-26 | 2026-09-02 | Issued for Approval (IFA) | EPCIC Contractor – Electrical Engineering | 1 | General | Lighting | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DWG-0002 | Process and Utilities Area Lighting Layout | Electrical | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 2 | Process & Utilities | Lighting | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DWG-0003 | Buildings Lighting and Small Power Layout | Electrical | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 1 | Buildings | Lighting & Small Power | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DWG-0004 | Hazardous Area Electrical Equipment Layout | Electrical | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 1 | Process Area | Hazardous Areas | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DWG-0005 | Electrical Equipment Location Layout | Electrical | Drawing | 2026-08-26 | 2026-09-02 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 1 | Site-wide | Power Distribution | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DWG-0006 | Underground Electrical Cable Routing Layout | Electrical | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 2 | Site-wide | Cable Routing | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DWG-0007 | Aboveground Cable Tray Routing Layout | Electrical | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 2 | Site-wide | Cable Routing | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-SCH-0001 | Power and Control Cable Schedule | Electrical | Schedule | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 2 | General | Cables | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-SCH-0002 | Cable Termination and Glanding Schedule | Electrical | Schedule | 2026-09-09 | 2026-09-16 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 1 | General | Cables | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DWG-0008 | Typical Electrical Installation Details | Electrical | Drawing | 2026-09-02 | 2026-09-09 | Approved for Construction (AFC) | EPCIC Contractor – Electrical Engineering | 1 | Site-wide | Electrical Installation | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-DAT-0001 | Medium Voltage Switchgear Datasheet | Electrical | Datasheet | 2026-08-12 | 2026-08-19 | Issued for Procurement (IFP) | EPCIC Contractor – Electrical Engineering | 1 | Electrical Substation | MV Distribution | WP-02 Procurement
HMK-26-01-ELE-DAT-0002 | Low Voltage Switchgear and MCC Datasheet | Electrical | Datasheet | 2026-08-12 | 2026-08-19 | Issued for Procurement (IFP) | EPCIC Contractor – Electrical Engineering | 1 | Electrical Substation | LV Distribution | WP-02 Procurement
HMK-26-01-ELE-DAT-0003 | Power Transformer Datasheet | Electrical | Datasheet | 2026-08-12 | 2026-08-19 | Issued for Procurement (IFP) | EPCIC Contractor – Electrical Engineering | 1 | Electrical Substation | Power Transformers | WP-02 Procurement
HMK-26-01-ELE-DAT-0004 | UPS and Battery Charger Datasheet | Electrical | Datasheet | 2026-08-19 | 2026-08-26 | Issued for Procurement (IFP) | EPCIC Contractor – Electrical Engineering | 1 | Electrical Substation | DC & UPS | WP-02 Procurement
HMK-26-01-ELE-DAT-0005 | Emergency Generator Datasheet | Electrical | Datasheet | 2026-08-19 | 2026-08-26 | Issued for Procurement (IFP) | EPCIC Contractor – Electrical Engineering | 1 | Utilities | Emergency Power | WP-02 Procurement
HMK-26-01-ELE-SPE-0001 | Power and Control Cable Specification | Electrical | Specification | 2026-08-19 | 2026-08-26 | Issued for Procurement (IFP) | EPCIC Contractor – Electrical Engineering | 1 | General | Cables | WP-02 Procurement
HMK-26-01-ELE-SPE-0002 | Lighting Fixtures, Receptacles and Junction Boxes Specification | Electrical | Specification | 2026-08-19 | 2026-08-26 | Issued for Procurement (IFP) | EPCIC Contractor – Electrical Engineering | 1 | General | Lighting & Small Power | WP-02 Procurement
HMK-26-01-ELE-REQ-0001 | Requisition – MV and LV Switchgear and MCC | Electrical | Requisition | 2026-08-19 | 2026-08-26 | Issued for Purchase | EPCIC Contractor – Electrical Engineering | 2 | Electrical Substation | Power Distribution | WP-02 Procurement
HMK-26-01-ELE-REQ-0002 | Requisition – Power Transformers | Electrical | Requisition | 2026-08-19 | 2026-08-26 | Issued for Purchase | EPCIC Contractor – Electrical Engineering | 1 | Electrical Substation | Power Transformers | WP-02 Procurement
HMK-26-01-ELE-REQ-0003 | Requisition – UPS and DC System | Electrical | Requisition | 2026-08-26 | 2026-09-02 | Issued for Purchase | EPCIC Contractor – Electrical Engineering | 1 | Electrical Substation | DC & UPS | WP-02 Procurement
HMK-26-01-ELE-REQ-0004 | Requisition – Emergency Generator | Electrical | Requisition | 2026-08-26 | 2026-09-02 | Issued for Purchase | EPCIC Contractor – Electrical Engineering | 1 | Utilities | Emergency Power | WP-02 Procurement
HMK-26-01-ELE-REQ-0005 | Requisition – Bulk Cables, Trays and Earthing Materials | Electrical | Requisition | 2026-09-02 | 2026-09-09 | Issued for Purchase | EPCIC Contractor – Electrical Engineering | 2 | Site-wide | Electrical Bulk | WP-02 Procurement
HMK-26-01-ELE-MTO-0001 | Electrical Bulk Material Take-Off | Electrical | Material Take-Off | 2026-09-02 | 2026-09-09 | Issued for Procurement (IFP) | EPCIC Contractor – Electrical Engineering | 2 | Site-wide | Electrical Bulk | WP-02 Procurement
HMK-26-01-ELE-PRC-0001 | Electrical Equipment and Cable Installation Procedure | Electrical | Procedure | 2026-09-16 | 2026-09-23 | Issued for Construction (IFC) | EPCIC Contractor – Electrical Engineering | 1 | General | Project-wide | WP-05 Electrical Engineering & Construction
HMK-26-01-ELE-PRC-0002 | Electrical Testing, Energisation and Commissioning Procedure | Electrical | Procedure | 2026-09-30 | 2026-10-07 | Issued for Commissioning | EPCIC Contractor – Electrical Engineering | 2 | General | Project-wide | WP-07 Commissioning & Handover
HMK-26-01-ELE-MAN-0001 | Electrical Systems Operation and Maintenance Manual | Electrical | Manual | 2026-10-14 | 2026-10-21 | Issued for Operations | EPCIC Contractor – Electrical Engineering | 2 | General | Project-wide | WP-07 Commissioning & Handover

## Instructions
How to import an MDR into EngiCite | How to import an MDR into EngiCite | How to import an MDR into EngiCite | How to import an MDR into EngiCite | How to import an MDR into EngiCite | How to import an MDR into EngiCite
Step | Instruction
1 | Open the MDR Import sheet and enter one planned deliverable per row.
2 | Do not rename the required headings or add formulas to import cells.
3 | Discipline and Document Type must match an active EngiCite category name or short code.
4 | Use real Excel dates or YYYY-MM-DD. Planned Final Date cannot precede the submission date.
5 | Progress Weight is optional and defaults to 1. Valid values are greater than 0 and no more than 1000.
6 | Save as .xlsx, upload it in the MDR, review the preview, then confirm import.
Example field | Example value
Document Number | CRX-PRO-PFD-0001
Planned Submission Date | 2026-09-30
Progress Weight | 1

## Allowed Values
Common Disciplines | Common Document Types | Issue Statuses
Process | Drawing | Draft / Work in Progress
Piping | Datasheet | Issued for Internal Review
Mechanical | Specification | Issued for Interdiscipline Check (IDC)
Civil | Calculation | Issued for Review (IFR)
Structural | Report | Issued for Client Review
Electrical | Procedure | Issued for Comment
Instrumentation | Requisition | Issued for Approval (IFA)
Telecommunications | Material Take-Off | Approved / Final
HSE | Schedule | Issued for Design (IFD)
Project | List | Issued for Tender (IFT)
Document Control | Philosophy | Issued for Bid (IFB)
| Manual | Issued for Quotation (IFQ)
Issued for Procurement (IFP)
Issued for Purchase
Issued for Vendor Approval
Issued for Manufacture (IFM)
Issued for Fabrication (IFF)
Approved for Construction (AFC)
Issued for Construction (IFC)
Issued for Installation
Issued for Site Use
Issued for Commissioning
Issued for Start-up
Issued for Operations
Issued for Information (IFI)
Issued for Coordination
Issued for HAZOP Review
Issued for Safety Review
Issued for Regulatory Approval
Redline / Marked-up As-Built
As-Built
Final As-Built
Issued for Handover
Approved for Handover
Final Documentation
Record / Reference
Superseded
Cancelled
Void / Withdrawn